## netwrkcapm
Activity | Duration(days) | Predecessor(s)
Project initiation | 3 | -
Analysis and planning | 15 | Project initiation
Design and user experience | 30 | Analysis and planning
Development / Coding | 65 | Design and user experience
App store submission and launch | 48 | Development / Coding
Post-launch and maintenance | 18 | App store submission and launch